Healthcare RAG — 14-Week Project Plan

eyouth × DEPI Microsoft Machine Learning Track  |  2025–2026

Team: Abdelrahman · Ziad · Youssef · Doha · Eman

Sat Mar 14 – Fri Jun 20, 2026  |  Weeks run Saturday → Friday  |  4-week buffer reserved Jun 21 – Jul 18

Milestone Overview

| Weeks | Dates | Milestone | Key Deliverable |
| --- | --- | --- | --- |
| W1–W2 | Mar 14 – Mar 27 | M1: Data Collection & Preprocessing | Cleaned corpus, EDA report |
| W3–W5 | Mar 28 – Apr 17 | M2: RAG Pipeline & Model Development | RAG pipeline, BLEU/ROUGE report |
| W6–W7 | Apr 18 – May 1 | M3: Azure Deployment | Live Azure URL, Docker, Streamlit |
| W8–W9 | May 2 – May 15 | M4: MLOps & Monitoring | MLflow logs, dashboard, KPIs |
| W10–W14 | May 16 – Jun 20 | M5: Final Documentation & Submission | Report, deck, submission |

Buffer: Jun 21 – Jul 18 (4 weeks) reserved for exams, delays, or revisions. Program ends ~Jul 22.

Week 1: Project Setup & Dataset Loading

Sat Mar 14 – Fri Mar 20

Milestone 1 — Data Collection & Preprocessing

Track session: Track: Deep Learning sessions ongoing this week

Team meeting: Fri Mar 20 — async check-in: confirm repo access and dataset loaded by everyone.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Create GitHub repo, define folder structure (data/, notebooks/, api/, dashboard/), add README, invite all 4 members. |
| Ziad | Load PubMedQA from HuggingFace, confirm schema (instruction / input / output), print first 10 rows, save locally. |
| Youssef | Explore dataset: check row count, column types, null values, duplicates. Write a short summary notebook. |
| Doha | Research Azure App Service free tier: RAM/CPU limits, cold-start behavior, deployment options. Write a 1-page note. |
| Eman | Set up MLflow locally, create experiment 'healthcare-rag', log a dummy run, confirm tracking UI works. |

Week Deliverables

- GitHub repo live and shared

- Dataset loaded and confirmed (10,000 rows)

- Dataset summary notebook

- Azure research note

- MLflow confirmed working

Week 2: Cleaning, EDA & Category Labelling

Sat Mar 21 – Fri Mar 27

Milestone 1 — Data Collection & Preprocessing

Track session: Track: Deep Learning sessions — project work runs in parallel

Team meeting: Fri Mar 27 — M1 review: EDA report and preprocessing pipeline complete and pushed to GitHub.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Clean dataset: remove duplicates, handle nulls, normalise text (lowercase, strip noise). Save cleaned CSV. |
| Ziad | Label all 10,000 queries into 6 categories (Symptoms, Diagnosis, Treatment, Medication, Prevention, General). Write labelling script. |
| Youssef | Run EDA: category distribution chart, query length histogram, response length stats. Export as notebook with charts. |
| Doha | Build a reusable preprocessing pipeline function: raw text to cleaned text. Document inputs, outputs, and steps. |
| Eman | Spot-check 100 random cleaned samples manually. Record data accuracy % for the KPI table in the proposal. |

Week Deliverables

- Cleaned corpus CSV

- 6-category label column confirmed

- EDA report notebook with charts

- Preprocessing pipeline script

- Data accuracy spot-check result (KPI)

Week 3: Embeddings & FAISS Vector Store

Sat Mar 28 – Fri Apr 3

Milestone 2 — RAG Pipeline & Model Development

Track session: Track: NLP sessions begin Mar 29 — directly relevant to embeddings work

Team meeting: Fri Apr 3 — sync: FAISS index built, embedding model chosen, retrieval tested with sample queries.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Generate embeddings for all 10,000 Q&A pairs using all-MiniLM-L6-v2. Save embeddings to disk as .npy file. |
| Ziad | Build FAISS index from saved embeddings. Test similarity search with 5 sample queries, inspect top-3 results. |
| Youssef | Generate BioBERT embeddings and compare retrieval quality vs all-MiniLM-L6-v2 on 20 queries. Log both in MLflow. |
| Doha | Split dataset: set aside 200 random pairs as held-out test set. Save as test_set.csv. Never use in training. |
| Eman | Draft LangChain RAG chain skeleton: query → embed → FAISS retrieve → context injection → prompt template. |

Week Deliverables

- FAISS index built and saved

- Embedding comparison logged in MLflow

- 200-query test set CSV

- LangChain RAG skeleton notebook

Week 4: Full RAG Pipeline & DistilBERT

Sat Apr 4 – Fri Apr 10

Milestone 2 — RAG Pipeline & Model Development

Track session: Track: NLP sessions Apr 5, Apr 8 — apply learnings directly to pipeline

Team meeting: Fri Apr 10 — sync: full RAG chain running end-to-end, DistilBERT training complete.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Complete LangChain RAG chain: retrieval + context injection + LLM generation. Test on 10 queries, inspect outputs. |
| Ziad | Add mandatory medical disclaimer to every RAG response. Bake into the chain — not a manual step. |
| Youssef | Fine-tune DistilBERT on the 6-category labelled dataset. Use 80/20 train/validation split. |
| Doha | Evaluate DistilBERT: generate classification report (F1, precision, recall per category). Target F1 >= 78%. |
| Eman | Log DistilBERT run in MLflow (params: epochs, lr, batch size; metrics: F1). Save best model checkpoint. |

Week Deliverables

- Full RAG pipeline notebook

- Disclaimer layer integrated

- DistilBERT trained + evaluated

- MLflow run logged

- Model checkpoint saved

Week 5: Evaluation: BLEU, ROUGE & FastAPI

Sat Apr 11 – Fri Apr 17

Milestone 2 — RAG Pipeline & Model Development

Track session: Track: NLP sessions Apr 12, Apr 15 — BLEU/ROUGE covered in track material

Team meeting: Fri Apr 17 — M2 review: evaluation report ready, FastAPI running locally, >= 5 MLflow runs logged.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Run full RAG pipeline on all 200 held-out test queries. Save outputs to rag_outputs.csv. |
| Ziad | Run plain LLM baseline (no retrieval) on the same 200 queries. Save to baseline_outputs.csv. |
| Youssef | Compute BLEU and ROUGE-L for both RAG and baseline. Build comparison table. Target: ROUGE-L >= 0.38. |
| Doha | Build FastAPI app: POST /query (returns answer + category + disclaimer + sources), GET /health. Test locally. |
| Eman | Write evaluation report: metrics table + 3-5 examples showing where RAG beats the baseline. |

Week Deliverables

- RAG + baseline output CSVs

- BLEU/ROUGE-L comparison report

- FastAPI app running locally

- Model evaluation report

- >= 5 MLflow runs logged

Week 6: Docker & Full Integration

Sat Apr 18 – Fri Apr 24

Milestone 3 — Azure Deployment

Track session: Track: Computer Vision sessions — project work runs independently

Team meeting: Fri Apr 24 — Docker dry-run: container runs cleanly on everyone's machine.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Integrate DistilBERT classifier into FastAPI: auto-tag query category on every POST /query. |
| Ziad | Integrate full RAG pipeline into FastAPI: single request returns category + answer + disclaimer + sources. |
| Youssef | Write Dockerfile. Build image locally. Run container, test all endpoints (POST /query, GET /health). |
| Doha | Benchmark local container latency: run 20 requests, record average. Flag anything over 5,000ms. |
| Eman | Write integration doc: end-to-end pipeline description, API input/output schema, how to run locally. |

Week Deliverables

- Integrated FastAPI app (classifier + RAG + disclaimer)

- Dockerfile + working local container

- Local latency benchmark

- Integration documentation

Week 7: Azure Deployment & Live URL

Sat Apr 25 – Fri May 1

Milestone 3 — Azure Deployment

Track session: Track: Computer Vision continues — Azure sessions start May 3 (next week)

Team meeting: Fri May 1 — M3 review: live Azure URL confirmed, proposal updated, Streamlit connected.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Push Docker image to Azure Container Registry. Deploy to Azure App Service. Confirm live URL responds. |
| Ziad | Test all API endpoints on the live Azure URL. Record warm-instance latency. Target <= 5,000ms. |
| Youssef | Enable Azure App Service health monitoring. Screenshot uptime dashboard for KPI evidence. |
| Doha | Connect Streamlit dashboard to live API: query count, category distribution, avg response latency. |
| Eman | CRITICAL: Paste the live Azure URL into the proposal document the moment deployment is confirmed. Do not wait. |

Week Deliverables

- Live Azure URL confirmed and working

- Proposal updated with Azure URL

- Latency benchmark (Azure warm instance)

- Streamlit dashboard connected to live API

Week 8: Deployment Hardening & MLflow Audit

Sat May 2 – Fri May 8

Milestone 4 — MLOps & Monitoring

Track session: Track: Azure sessions May 3, May 6 — attend and apply to deployment work

Team meeting: Fri May 8 — sync: deployment stable, MLflow runs complete, dashboard showing all KPIs.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Run 100-request stress test on live Azure URL. Record pass/fail and latency distribution. |
| Ziad | Audit all MLflow runs. Ensure >= 5 documented runs with clear param/metric logging. Add any missing. |
| Youssef | Add BLEU and ROUGE-L scores to MLflow for every model configuration tested. |
| Doha | Conduct hallucination review: manually review 30 random RAG responses. Target <= 15% hallucination rate. |
| Eman | Polish Streamlit dashboard: KPI cards for query volume, category split, avg latency, F1, ROUGE-L. |

Week Deliverables

- Stress test report

- >= 5 MLflow runs fully logged with metrics

- Hallucination review (30 responses)

- Polished Streamlit dashboard

Week 9: Monitoring, KPIs & Documentation

Sat May 9 – Fri May 15

Milestone 4 — MLOps & Monitoring

Track session: Track: Azure session May 10 — attend, then return to documentation work

Team meeting: Fri May 15 — M4 review: all monitoring docs final, GitHub notebooks cleaned.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Verify Azure uptime over past 2 weeks. Screenshot Azure monitor. Confirm >= 90% target. |
| Ziad | Run auto-resolution rate test: % of 200 test queries answered without fallback. Target >= 60%. |
| Youssef | Finalise MLOps documentation: experiment tracking, monitoring, retraining strategy — one clean doc. |
| Doha | Clean GitHub repo: clear notebook outputs, remove debug cells, all notebooks run top-to-bottom. |
| Eman | Write business KPI impact section: auto-resolution rate, latency, hallucination rate, evaluator feedback plan. |

Week Deliverables

- Azure uptime report + screenshot

- Auto-resolution rate result

- MLOps documentation final

- GitHub notebooks cleaned

- Business KPI section written

Week 10: Final Report Writing

Sat May 16 – Fri May 22

Milestone 5 — Final Documentation & Presentation

Track session: Track: Coaching sessions this period — lighter week, good for deep writing

Team meeting: Fri May 22 — full report draft reviewed: each person checks all sections, not just their own.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Write: problem statement, objectives, dataset strategy, RAG pipeline architecture with diagram. |
| Ziad | Write: classification model design, training process, F1 results table, per-category breakdown. |
| Youssef | Write: data pipeline, EDA summary, preprocessing decisions, dataset statistics. |
| Doha | Write: deployment architecture, Azure setup, Docker config, API contract, security note. |
| Eman | Write: MLOps setup, MLflow log summary, monitoring approach, responsible AI considerations. |

Week Deliverables

- All report sections drafted — merge into one document by end of week

Week 11: Report Polish & Evaluation Section

Sat May 23 – Fri May 29

Milestone 5 — Final Documentation & Presentation

Track session: Track: Coaching sessions continue

Team meeting: Fri May 29 — final report ready for proofreading. No open sections.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Write: evaluation results section — BLEU/ROUGE-L table, RAG vs baseline comparison, analysis. |
| Ziad | Write: future enhancements roadmap (supplementary datasets, Azure Cognitive Search, retraining). |
| Youssef | Merge all sections into one document. Fix terminology consistency, figure numbering, formatting. |
| Doha | Full proofread: grammar, clarity, completeness. Fix any missing references or gaps. |
| Eman | Confirm all KPIs are evidenced in the report: screenshots, CSV results, MLflow logs attached. |

Week Deliverables

- Final report complete and proofread

- All KPIs evidenced with attachments

Week 12: Presentation Deck & Demo

Sat May 30 – Fri Jun 5

Milestone 5 — Final Documentation & Presentation

Track session: Track: English for Freelancing sessions — lighter, good for presentation prep

Team meeting: Fri Jun 5 — first full 15-minute rehearsal. Time it strictly. Log weak spots.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Build slides 1-8 (DEPI template): title, team, problem statement, approach, pipeline diagram. |
| Ziad | Build slides 9-15: model results (BLEU/ROUGE-L, F1), deployment architecture, KPI dashboard screenshots. |
| Youssef | Prepare live demo flow: POST /query on live Azure URL, walk through Streamlit dashboard. |
| Doha | Record backup demo video (screen recording) in case of internet issues on presentation day. |
| Eman | Prepare Q&A answer notes: why RAG, why PubMedQA, how to handle any KPI that missed target. |

Week Deliverables

- Presentation deck (DEPI template, 15-20 slides)

- Backup demo video

- Q&A answer notes

Week 13: Rehearsals & Final Polish

Sat Jun 6 – Fri Jun 12

Milestone 5 — Final Documentation & Presentation

Track session: Track: English for Freelancing sessions

Team meeting: Fri Jun 12 — second full rehearsal. All 5 members must know their speaking parts cold.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Incorporate feedback from first rehearsal into the presentation deck. |
| Ziad | Final report: last proofread pass. Confirm Azure URL is still live and in the proposal. |
| Youssef | Compile full submission package: report PDF, presentation PPTX, source code ZIP, GitHub link, Azure URL. |
| Doha | Final GitHub check: README with run instructions, all notebooks reproducible end-to-end. |
| Eman | Second full team rehearsal: 15 minutes + Q&A. Record it so everyone can review their delivery. |

Week Deliverables

- Presentation deck final version

- Submission package compiled

- Second rehearsal done and recorded

Week 14: Final Submission

Sat Jun 13 – Fri Jun 20

Milestone 5 — Final Documentation & Presentation

Track session: Track: Azure sessions resume Jun 21 — submit before then. 4-week buffer remains after.

Team meeting: Thu Jun 19 — final team check together. Submit by Fri Jun 20. Confirm receipt as a group.

Weekly Tasks

| Member | Task |
| --- | --- |
| Abdelrahman | Run the full system one final time: confirm live URL, all endpoints, and Streamlit dashboard still working. |
| Ziad | Package source code as ZIP: all notebooks, FastAPI app, Dockerfile, requirements.txt, .env.example. |
| Youssef | Submit via official DEPI submission form: report PDF, presentation PPTX, source ZIP, GitHub link, Azure URL. |
| Doha | Screenshot and share submission confirmation with the whole team. |
| Eman | Add project to each member's GitHub profile, LinkedIn, and CV. Project complete. |

Week Deliverables

- DEPI submission form submitted by Jun 20

- Submission confirmation screenshot shared

- Project on all team portfolios